## Instructions
#VALUE!
Missing stakeholders is a major hidden issue that may crop up when you least expect it. You can scan the QR code or click on the cell to read more details on the problems that arise with missed stakeholder assessments, and their potential solutions. This Stakeholder Analysis tool is designed to help customers ensure no stakeholder is missed during a major transformation project. It gives many suggested categories of stakeholders and allows for adding people in after sufficient internal brainstorming. After the identification process is complete, it uses the three parameters listed below to inform a communication strategy that can be followed throughout the project. Hovering over each type of stakeholder will also pop up suggestions on how to best select the right stakeholders. This tool is made available to all organizations at no-cost by Orbrick Consulting Pvt. Ltd. - an Oracle ERP Consulting Expert. |  | #VALUE!
Buy In | Impact of Change
How bought in is this individual to the Oracle Programme? Are they in synch and agreement with the details of the change? | How deeply will the project affect the group, in terms of a change to their working processes, practices and behaviour?
Influence Over Change
What is this individual's ability to influence the delivery of the project?
#VALUE!
Steps to build matrix:
1. List down your stakeholders under each suggested category in the SAData tab
2. Fill in the rating from 0 (low) - 5 (HIGH) against each metric
3. View the Stakeholder Map tab
4. Design communication strategy based on the suggested actions
If you need any help, you can book a no-cost advisory session with Orbrick Consulting.

## SAData
Stakeholder Group Mapping Tool
Stakeholder group | Stakeholder | High hevel description / Comments | No. of impacted stakeholders in group | Actions to feed into communication campaigns and plans | Owner | How bought into Project? HIGH (5) - low (0) | Impact of change HIGH (5) - low (0) | Influence over change HIGH (5) - low (0) | Last Updated
Programme Team | Project Coordinator |  |  |  |  | 3 | 3 | 3
| Programme Manager |  |  |  |  | 3 | 5 | 3
| IT Project Manager |  |  |  |  | 2 | 4 | 3
| Project News Anchor |  |  |  |  | 1 | 1 | 1
Corporate Functions / Key Users | HR Champion |  |  |  |  | 5 | 4 | 3
| IT Champion |  |  |  |  | 3 | 2 | 5
Supply Chain Champion
Planning Champion
Executive Governance / Steering Board | Programme Executive Sponsor |  |  |  |  | 4 | 5 | 2
Service Areas | Finance POC |  |  |  |  | 3 | 3 | 1
End Users
External Stakeholders | Vendor POC
Support Vendor POC
Note on A3: We suggest giving one person an anchor/reporter role who writes out progress notes to send out to larger teams in an engaging way. This helps avoid any surprises closer to go-live and increases adoption.
Note on A7: We suggest that the following points be taken into consideration when selecting your Key Users: 1. Digital Transformations will take a massive time commitment. Business as usual needs to be planned, ideally with a complete replacement for at least a few key users who will be fully part of the project team during the duration of the project. 2. Involve Change Agents. Involve motivated and influencial employees who talk to their peers throughout the project to sensitize people to the change and surface any early concerns. 3. Involve those with decision making authority. It is important that most decisions are taken "in the room". Delays will tumble over and have a compounding effect on the overall project timelines. 4. Involve people who understand the business well. These are people who are typically well tenured in the organization.
Note on A18: Executive Sponsorship is one of the key determinants of the success of the transformation project. Ideally, even the Sponsorship should be following a "Two-in-a-Box" model and you should have executive sponsors from the vendor's team as active participants in the project as well.
Note on A23: Think of all stakeholders that this project may affect. Which service areas may not be in the driving seat but will still be impacted or involved.
Note on A39: This could include other third party vendors (think integrations), change managers, suppliers, or anyone else who may have a direct impact (big or small) by the system change.

## Stakeholder Map
Quick Reference
Engage | Partner
Inform | Consult
* Look at results tab for actions

## Results
ENGAGE - High power and low interest - Engage and consult on interest area - Aim to move into upper right-hand quadrant - Stakeholders include senior managers and board members that are not impacted by a change in the core business systems Communication Strategy: - Ensure stakeholders clearly understand the project's purpose, vision, scope, schedule and approach - Engage stakeholders through one-on-one meetings to raise awareness of the project, to address their concerns and to communicate the impact and benefits of the project - May need to further engage stakeholders through process mapping and requirements gathering sessions - Keep stakeholders informed of project progress through weekly status reports | PARTNER - High power and high interest - Focus efforts on this group - Establish good working relationship with this group - Involve in decision making process - Engage and consult regularly - Stakeholders include sponsors and approving board members Communication Strategy: - Collaborate with stakeholders to define the project's purpose, vision, scope, schedule and approach - Obtain buy-in from stakeholders on key decisions - Escalate unresolved issues to risks to senior stakeholders if necessary - Provide detailed project updates as required (e.g. monthly updates, quarterly updates) - Keep stakeholders informed of project progress through weekly status reports
INFORM - Low power and low interest - May have some involvement but relatively low in priority - Inform via general communications - Aim to move into lower right-hand quadrant - Stakeholders include everyone else within the firm that is not directly involved in the project Communication Strategy: - Keep stakeholders informed of project progress through weekly status reports - Equip Line Managers with basic project information so they can address questions their direct reports may have (e.g. FAQ Document) | CONSULT - Low power and high interest - This group may be a source of risks - Stakeholders require careful monitoring and management - Stakeholders include business and IT SMEs Communication Strategy: - Ensure stakeholders clearly understand the project's purpose, vision, scope, schedule and approach - Engage stakeholders through the project kick-off and process mapping, requirements gathering and requirements prioritization sessions - Keep stakeholders informed of project progress through weekly status reports